ICTPMG613

Manage ICT project planning

Unit Assessment Pack (TAP)

Table of Contents

Assessment Pack (UAP) – Cover Sheet	3

Student and Trainer/Assessor Details	3

Course and Unit Details	3

Assessment Submission Method	3

Student Declaration	3

Assessment Plan	4

Unit information pack	4

UAT 1 – Unit Knowledge Test (UKT)	5

Pre-assessment checklist	5

Purpose	5

Information for students	5

Reasonable adjustments	5

Student declaration	5

Assessment task instructions	6

Unit Assessment Result Sheet (UARS)	17

UAT 2 – Unit Project (UP)	19

Pre-assessment checklist	19

Purpose	19

Information for students	19

Reasonable adjustments	19

Student declaration	19

Assessment task instructions	20

Unit Assessment Result Sheet (UARS)	39

Purpose of unit Assessment Pack This document is for the student and provides all the assessment tasks which need to be completed to be deemed competent in this unit. The document also provides instructions and information to assist the student to complete each assessment task. Students must respond to all questions and submit the assessment to their Assessor.

Copyright This document was developed by VET Resources © 2021. No part of this resources may be reproduced in any form or by any means, electronic or mechanical including photocopying or recording or by any information retrieval system without written permission from VET Resources. Legal action may be taken against any person who infringes their copyright through unauthorised copying.

# Assessment Pack (UAP) – Cover Sheet

## Student and Trainer/Assessor Details

| Student ID | 0000028926 |
| --- | --- |
| Student name | Muhammad Hammad Saleem |
| Trainer/Assessor name | Sandesh Bista |

## Course and Unit Details

| Course code |  |
| --- | --- |
| Course name |  |
| Unit code | ICTPMG613 |
| Unit name | Manage ICT project planning |

## Assessment Submission Method

| ☐ By hand to trainer/assessor | ☐ By email to trainer/assessor | ☐ Online submission via Learning Management System (LMS) |
| --- | --- | --- |
| ☐ By Australia Post to RTO | ☐ Any other method _________________________________________________ (Please mention here) |  |

## Student Declaration

- I certify that the work submitted for this assessment pack is my own. I have clearly referenced any sources used in my submission. I understand that a false declaration is a form of malpractice. - I have kept a copy of this assessment pack and all relevant notes, attachments, and reference material that I used in the production of the assessment pack; - For the purposes of assessment, I give the Trainer/Assessor of this assessment the permission to: - Reproduce this assessment and provide a copy to another member of staff; and - Take steps to authenticate the assessment, including communicating a copy of this assessment to a checking service (which may retain a copy of the assessment on its database for future plagiarism checking). Student signature; Date; 30/5/2026.

## Assessment Plan

To demonstrate competence in this unit, the student must be assessed as satisfactory in each of the following assessment tasks.

| Evidence recorded | Evidence Type/ Method of assessment |  |  | Sufficient evidence recorded/Outcome |
| --- | --- | --- | --- | --- |
| Unit Assessment Task 1 | Unit Knowledge Test (UKT) |  |  | S / NS (First Attempt) S / NS (Second Attempt) |
| Unit Assessment Task 2 | Unit Project (UP) |  |  | S / NS (First Attempt) S / NS (Second Attempt) |
| Final result | C ☐ NYC ☐ | Date assessed |  |  |
|  |  | Trainer/Assessor Signature |  |  |

## Unit information pack

The student and Trainer/Assessor must read and understand all the information in the unit information pack before completing the unit assessment pack.

|  | # UAT 1 – Unit Knowledge Test (UKT) |
| --- | --- |

## Pre-assessment checklist

## Purpose

The pre-assessment checklist helps students determine if they are ready for assessment. The Trainer/Assessor must review the checklist with the student before the student attempts the assessment task. If any items of the checklist are incomplete or not clear to the student, the Trainer/Assessor must provide relevant information to the student to ensure they understand the requirements of the assessment task. The student must ensure they are ready for the assessment task before undertaking it.

## Information for students

- Please make sure you have completed the necessary prior learning before attempting this assessment.

- Please make sure your Trainer/Assessor has clearly explained the assessment process and tasks to be completed.

- Please make sure you understand what evidence is required to be collected and how.

- Please make sure you know your rights and the complaints and appeal process.

- Please make sure you discuss any special needs or reasonable adjustments to be considered during the assessment (refer to the Reasonable Adjustments Strategy Matrix and negotiate these with your Trainer/Assessor).

- Please make sure that you have access to a computer and the internet (if you prefer to type the answers).

- Please ensure that you have all the required resources needed to complete this Unit Assessment Task (UAT).

- Due date of this assessment task is according to your timetable.

- In exceptional (compelling and compassionate) circumstances, an extension to submit an assessment can be granted by the Trainer/Assessor.

- Evidence of the compelling and compassionate circumstances must be provided together with your request for an extension to submit your assessment work.

- Request for an extension to submit your assessment work must be made before the due date of this assessment task.

## Reasonable adjustments

- If student has requested a reasonable adjustment, then complete the reasonable adjustment form included in the unit information pack.

## Student declaration

- I confirm that Trainer/Assessor has provided all the information related to the assessment task as included in the information for student section and I am ready for the assessment.

| Student signature |  | Date | 30/5/2026 |
| --- | --- | --- | --- |

|  | ## Assessment task instructions |
| --- | --- |

Assessment type:

- Written Questions

Instructions provided to the student:

Assessment task description:

- This is the first (1) unit of assessment task that the student must successfully complete to be deemed competent in this unit of competency.

- The Unit Knowledge Test is comprised of sixteen (16) written questions.

- Student must respond to all the questions and submit them to the Trainer/Assessor.

- Student must answer all questions to the required level, e.g. provide the number of points, to be deemed satisfactory in this task.

- Trainer/Assessor is required to provide feedback within two weeks and notify students when results are available.

Applicable conditions:

- This knowledge test is untimed and is conducted as an open book test (this means student can refer to textbooks during the test).

- Student must read and respond to all questions.

- Student may handwrite/use computers to answer the questions.

- Student must complete the task independently.

- No marks or grades are allocated for this assessment task. The outcome of the task will be Satisfactory or Not Satisfactory.

- Trainer /Assessor must assess student’s written skills and knowledge as he/she completes this assessment task.

- The Trainer/Assessor may ask the student relevant questions on this assessment task to ensure that this is his/her own work.

Resubmissions and reattempts:

- Where a student’s answers are deemed not satisfactory after the first attempt, a resubmission attempt will be allowed.

- Student may speak to their Trainer/Assessor if the student has any difficulty in completing this task and requires a reasonable adjustment (e.g., can be given as an oral assessment).

- For more information, please refer to the RTO Student Handbook.

Location:

- This assessment task may be completed in (tick the relevant box):

| ☐ Learning Management System | ☐ Classroom |
| --- | --- |
| ☐ Simulated learning environment | ☐ Workplace |
| Other: ____________________________________ |  |

- Trainer/Assessor will provide the student with further information regarding the location for completing this assessment task.

Purpose of the assessment

The purpose of the assessment is to check knowledge relevant to the unit.

Instructions for answering written questions:

- Students must complete a written assessment consisting of a series of questions.

- It is expected from students to correctly answer all the questions.

- Answers must demonstrate an understanding and application of relevant concepts, critical thinking, and good writing skills.

- Students must respond to all questions for this assessment in a concise manner, providing only information that is relevant.

- Student must use non-discriminatory language. The language should not devalue, demean, or exclude individuals or groups on the basis of such attributes including gender, disability, culture, race, religion, sexual preference, age and/or any other basis. Gender inclusive language should be used.

- Assessors must not accept responses/answers that have been copied directly from other sources materials.

|  | Resources required to complete the assessment task: |
| --- | --- |

- Computer

- Internet

- MS Word

- Learner guide

- PowerPoint presentation

- Unit Assessment Pack (UAP)

- Access to other learning materials such as textbooks

| Question 1: Briefly explain any two estimation techniques and methods used in project planning. Answer within 50 – 100 words. | Satisfactory response |  |
| --- | --- | --- |
|  | Yes ☐ | No ☐ |

Analogous Estimation Analogous estimation uses information from previous similar projects to estimate the cost, duration, or resources of a new project. Project managers compare project size, complexity, and scope with historical data to make quick estimates. This technique is useful in early planning stages when detailed information is limited. It is faster and less costly, but accuracy depends on the similarity between past and current projects. Bottom-Up Estimation Bottom-up estimation divides the project into smaller tasks and estimates the cost and time of each activity individually. These estimates are then combined to determine the total project estimate. This method provides higher accuracy because it considers detailed work components. However, it requires more time, effort, and detailed project information during planning.

| Question 2: Briefly explain any two planning techniques and methods which can be used in project management. Answer within 80 – 120 words. | Satisfactory response |  |
| --- | --- | --- |
|  | Yes ☐ | No ☐ |

Gantt Chart A Gantt chart is a project planning technique used to schedule and monitor project activities over a specific timeline. It presents tasks in a bar chart format, showing the start date, finish date, duration, and dependencies between activities. Project managers use Gantt charts to allocate resources, track progress, and identify delays. This method improves coordination among team members and helps ensure that project milestones are achieved on time. It is widely used because it provides a clear visual overview of the entire project schedule. Critical Path Method (CPM) The Critical Path Method (CPM) is a planning technique used to identify the sequence of activities that directly affect project completion time. It calculates the longest path of dependent tasks and highlights critical activities that cannot be delayed without impacting the overall project deadline. CPM helps project managers prioritize important tasks, manage time efficiently, and allocate resources effectively. It also supports risk management by identifying areas where delays may occur and assists in maintaining project schedules within planned timeframes.

| Question 3. Briefly explain any two project management methodologies. Answer within 100 – 150 words. | Satisfactory response |  |
| --- | --- | --- |
|  | Yes ☐ | No ☐ |

Waterfall Methodology Waterfall is a traditional project management methodology where project activities are completed in a sequential order. Each phase, such as planning, design, implementation, testing, and maintenance, must be finished before moving to the next stage. This approach is suitable for projects with clear requirements and limited changes, such as construction or manufacturing projects. Waterfall provides strong documentation, structured processes, and easy progress tracking. However, it offers limited flexibility because changes made after project execution can increase cost and delay completion. Agile Methodology Agile is a flexible project management methodology that focuses on continuous improvement, collaboration, and customer feedback. Projects are divided into small phases called iterations or sprints, allowing teams to deliver work gradually and adapt to changing requirements. Agile encourages frequent communication between stakeholders and project teams to improve product quality and customer satisfaction. This methodology is commonly used in software development and technology projects because it supports innovation, quick problem-solving, and faster delivery of project outcomes.

| Question 4: Briefly explain any two system development methodologies. Answer within 50 – 100 words. | Satisfactory response |  |
| --- | --- | --- |
|  | Yes ☐ | No ☐ |

System Development Life Cycle (SDLC) The System Development Life Cycle (SDLC) is a structured methodology used to develop information systems through defined stages such as planning, analysis, design, implementation, testing, and maintenance. It ensures systematic development, proper documentation, and quality control throughout the project. SDLC is suitable for large projects where requirements are clearly defined and stability is important. Rapid Application Development (RAD) Rapid Application Development (RAD) is a system development methodology that focuses on quick development and user feedback. It uses prototypes and iterative improvements to speed up system creation. RAD encourages active user involvement and flexibility in design changes. This methodology is suitable for projects requiring fast delivery and adaptable system requirements.

| Question 5: Answer the following: A.) What role do business needs play in project management? Answer within 40 – 60 words. B.) Why is project control important in project management? Answer within 20 – 40 words. C.) What is the role of ROI in project management? Answer within 40 – 80 words. | Satisfactory response |  |
| --- | --- | --- |
|  | A.) Yes ☐ B.) Yes ☐ C.) Yes ☐ | No ☐ No ☐ No ☐ |

A.) Role of Business Needs in Project Management Business needs provide the foundation and direction for a project. They help define project objectives, scope, priorities, and expected outcomes. Understanding business needs ensures that project activities align with organizational goals and deliver value to stakeholders while solving specific operational or strategic problems. B.) Importance of Project Control in Project Management Project control is important because it helps monitor project performance, manage risks, control costs, and ensure activities remain on schedule. It supports timely corrective actions to achieve project objectives successfully. C.) Role of ROI in Project Management Return on Investment (ROI) helps evaluate the financial benefits of a project compared to its costs. It supports decision-making by identifying whether a project is financially worthwhile and contributes value to the organization. Project managers use ROI to prioritize projects, justify investments, and measure project success after completion.

| Question 6: Explain the project management plan. List the sections that should be included in the project management plan. Answer within 50 – 100 words. | Satisfactory response |  |
| --- | --- | --- |
|  | Yes ☐ | No ☐ |

A project management plan is a formal document that defines how a project will be executed, monitored, and controlled from start to finish. It serves as a roadmap for the project team by outlining objectives, scope, timelines, resources, and risk management strategies to ensure successful delivery. Key sections include: project scope statement, schedule/timeline, cost management plan, resource plan, risk management plan, communication plan, quality management plan, stakeholder management plan, and change control procedures.

| Question 7: How can the documents be stored in project management? | Satisfactory response |  |
| --- | --- | --- |
|  | Yes ☐ | No ☐ |

Documents in project management can be stored using both physical and digital systems. Traditionally, they may be kept in organized filing cabinets with proper labeling for easy retrieval. However, modern project management mainly uses digital storage such as cloud-based platforms (e.g., Google Drive, SharePoint, or project management software). These systems allow centralized access, version control, backup, and secure sharing among team members. Proper document management ensures accuracy, transparency, and easy tracking of project information throughout the project lifecycle.

| Question 8: What are the six steps that are taken to assess project management methodologies? | Satisfactory response |  |
| --- | --- | --- |
|  | Yes ☐ | No ☐ |

Six steps used to assess project management methodologies are: - Define project requirements: Identify objectives, scope, and constraints. - Analyse project complexity: Evaluate size, risk level, and uncertainty. - Evaluate methodology options: Compare methods such as Agile, Waterfall, or hybrid approaches. - Assess resource availability: Consider time, budget, skills, and tools. - Match methodology to project needs: Select the approach that best fits project characteristics. - Review and validate choice: Confirm suitability with stakeholders and adjust if necessary.

| Question 9. What is meant by product development, and what steps are involved in product development? Answer within 50-80 words. | Satisfactory response |  |
| --- | --- | --- |
|  | Yes ☐ | No ☐ |

Product development is the process of creating or improving a product to meet customer needs and market demand. It involves transforming an idea into a usable and market-ready product. The main steps include idea generation, idea screening, concept development and testing, business analysis, product design and development, testing, and finally commercialisation or launch. These steps ensure the product is viable, functional, and aligned with customer expectations before entering the market.

| Question 10. What are the five steps involved in the selection of the right project management methodology? | Satisfactory response |  |
| --- | --- | --- |
|  | Yes ☐ | No ☐ |

The five steps involved in selecting the right project management methodology are: - Understand project requirements – Define goals, scope, and deliverables clearly. - Assess project characteristics – Evaluate complexity, risk, size, and uncertainty. - Identify available methodologies – Consider options such as Agile, Waterfall, or hybrid approaches. - Evaluate organisational constraints – Review budget, time, resources, and team capability. - Select and validate methodology – Choose the most suitable approach and confirm with stakeholders for alignment.

| Question 11. What is project scheduling? Answer within 40 – 70 words. | Satisfactory response |  |
| --- | --- | --- |
|  | Yes ☐ | No ☐ |

Project scheduling is the process of planning and organizing project activities over a specific timeline. It involves determining task sequences, durations, start and finish dates, and resource allocation. Scheduling helps ensure that project work is completed in a logical order, within deadlines, and with efficient use of resources. It also supports monitoring progress and identifying delays to keep the project on track.

| Question 12. Explain work packages in the planning project. Answer within 30 – 50 words. | Satisfactory response |  |
| --- | --- | --- |
|  | Yes ☐ | No ☐ |

Work packages are the smallest units of work in a project’s Work Breakdown Structure (WBS). They group related tasks that can be assigned, estimated, and managed easily. Work packages help in planning, cost estimation, scheduling, and monitoring project progress more effectively.

| Question 13: What is project monitoring, and how it can be done? Answer within 50 – 100 words. | Satisfactory response |  |
| --- | --- | --- |
|  | Yes ☐ | No ☐ |

Project monitoring is the process of tracking a project’s progress to ensure it is meeting its objectives, timeline, budget, and quality standards. It helps identify deviations early so corrective actions can be taken. It can be done through regular progress reports, performance indicators (KPIs), milestone tracking, and meetings with stakeholders. Tools such as Gantt charts, dashboards, and project management software are also used to compare actual performance against the planned schedule and budget.

| Question 14: What is cash flow, and how it can be calculated? Answer within 100 – 150 words. | Satisfactory response |  |
| --- | --- | --- |
|  | Yes ☐ | No ☐ |

Cash flow refers to the movement of money in and out of a project or business over a specific period. It shows how much cash is generated (inflows) and how much is spent (outflows). Positive cash flow means more money is coming in than going out, while negative cash flow indicates higher expenses than income. Cash flow is calculated by subtracting total cash outflows from total cash inflows: Cash Flow = Total Inflows − Total Outflows Inflows include revenues, investments, or funding, while outflows include costs such as materials, labour, and overheads. Monitoring cash flow helps ensure the project remains financially viable and can meet its obligations on time.

| Question 15: What are the five steps involved in the development of a project budget? | Satisfactory response |  |
| --- | --- | --- |
|  | Yes ☐ | No ☐ |

The five steps involved in the development of a project budget are: - Define project scope – Identify all project objectives, deliverables, and required activities. - Estimate costs – Calculate costs for labour, materials, equipment, and other resources. - Allocate resources – Assign financial resources to specific tasks and phases. - Add contingencies – Include allowances for risks, uncertainties, and unexpected expenses. - Review and finalise budget – Validate the budget with stakeholders and approve it for implementation

| Question 16: List any five methods by which the project budget can be monitored. | Satisfactory response |  |
| --- | --- | --- |
|  | Yes ☐ | No ☐ |

Five methods to monitor a project budget are: - Variance Analysis – Comparing actual costs with the planned budget to identify deviations. - Earned Value Management (EVM) – Measuring project performance by integrating cost, schedule, and scope. - Cost Reports – Regular financial reports showing spending status and trends. - Budget Tracking Software – Using tools like spreadsheets or project management systems to monitor expenses in real time. - Milestone Reviews – Checking budget usage at key project stages to ensure financial control.

|  |  | # Unit Assessment Result Sheet (UARS) |  |
| --- | --- | --- | --- |
| Outcome of Unit Assessment Task (UAT) |  | First attempt:. Outcome (please make sure to tick the correct checkbox): Satisfactory (S) ☐ or Not Satisfactory (NS) ☐ Date: _______(day)/ _______(month)/ ____________(year) Second attempt:. Outcome (please make sure to tick the correct checkbox): Satisfactory (S) ☐ or Not Satisfactory (NS) ☐ Date: _______(day)/ _______(month)/ ____________(year) |
| Feedback to Student |  | - First attempt:. - Second attempt:. |
| Student Declaration |  | - I declare that the answers I have provided are my own work. Where I have accessed information from other sources, I have provided references and or links to my sources. - I have kept a copy of all relevant notes and reference material that I used as part of my submission. - I have provided references for all sources where the information is not my own. I understand the consequences of falsifying documentation and plagiarism. I understand how the assessment is structured. I accept that all work I submit must be verifiable as my own. - I understand that if I disagree with the assessment outcome, I can appeal the assessment process, and either re-submit additional evidence undertake gap training and or have my submission re-assessed. - All appeal options have been explained to me. |  |
| Student Signature |  |  |  |
| Date |  | 30/05/2026 |  |
| Trainer/Assessor Name |  |  |  |
| Trainer/Assessor Declaration |  | I hold: Vocational competencies at least to the level being delivered Current relevant industry skills Current knowledge and skills in VET, and undertake Ongoing professional development in VET I declare that I have conducted an assessment of this candidate’s submission. The assessment tasks were deemed current, sufficient, valid, and reliable. I declare that I have conducted a fair, valid, reliable, and flexible assessment. I have provided feedback to the above-named candidate. |  |
| Trainer/Assessor Signature |  |  |  |
| Date |  |  |  |
| Office Use Only |  | Outcome of Assessment has been entered onto the Student Management System on _________________ (insert date) by (insert Name) __________________________________ |  |

|  | # UAT 2 – Unit Project (UP) |
| --- | --- |

## Pre-assessment checklist

## Purpose

The pre-assessment checklist helps students determine if they are ready for assessment. The Trainer/Assessor must review the checklist with the student before the student attempts the assessment task. If any items of the checklist are incomplete or not clear to the student, the Trainer/Assessor must provide relevant information to the student to ensure they understand the requirements of the assessment task. The student must ensure they are ready for the assessment task before undertaking it.

## Information for students

- Please make sure you have completed the necessary prior learning before attempting this assessment.

- Please make sure your Trainer/Assessor has clearly explained the assessment process and tasks to be completed.

- Please make sure you understand what evidence is required to be collected and how.

- Please make sure you know your rights and the complaints and appeal process.

- Please make sure you discuss any special needs or reasonable adjustments to be considered during the assessment (refer to the Reasonable Adjustments Strategy Matrix and negotiate these with your Trainer/Assessor).

- Please make sure that you have access to a computer and the internet (if you prefer to type the answers).

- Please ensure that you have all the required resources needed to complete this Unit Assessment Task (UAT).

- Due date of this assessment task is according to your timetable.

- In exceptional (compelling and compassionate) circumstances, an extension to submit an assessment can be granted by the Trainer/Assessor.

- Evidence of the compelling and compassionate circumstances must be provided together with your request for an extension to submit your assessment work.

- Request for an extension to submit your assessment work must be made before the due date of this assessment task.

## Reasonable adjustments

- If a student requires a reasonable adjustment, then complete the reasonable adjustment form included in the unit information pack.

## Student declaration

- I confirm that the Trainer/Assessor has provided all the information related to the assessment task as included in the information for student section and I am ready for the assessment.

| Student signature |  | Date | 30/5/2026 |
| --- | --- | --- | --- |

|  | ## Assessment task instructions |
| --- | --- |

Assessment type:

- Unit Project

Instructions provided to the student:

Assessment task description:

- This is the second (2) unit assessment task that student has to successfully complete to be deemed competent in this unit of competency.

- The student is required to complete three activities.

  - Activity 1: Project management plan

  - Activity 2: Selection of project methodology and modification of the schedule

  - Activity 3: Budget planning and progress of the project

- The student must attempt all criteria to the required level, e.g., Assessment criteria mentioned in the performance checklist to be deemed satisfactory in this task.

Applicable conditions:

- Activity 1, 2, and 3 are untimed and conducted as an open book test (this means the student can refer to textbooks or other learner materials during the test).

- The student must complete the task independently.

- No marks or grades are allocated for this assessment task. The outcome of the task will be Satisfactory or Not Satisfactory.

- Trainer /Assessor must assess student’s practical skills, technique, and knowledge as he/she completes this assessment task.

- The Trainer/Assessor may ask the student relevant questions on this assessment task to ensure that this is his/her own work.

Resubmissions and reattempts:

- Where a student’s performance is deemed not satisfactory after the first attempt, a resubmission attempt will be allowed. Assessor must note any such submissions.

- Student may speak to their Trainer/Assessor if the student has any difficulty in completing this task and requires a reasonable adjustment (e.g., can be given as an oral assessment).

- For more information, please refer to the RTO Student Handbook.

Location:

- This assessment task may be completed in (tick the relevant box):

| ☐ Learning Management System | ☐ Classroom |
| --- | --- |
| ☐ Simulated learning environment | ☐ Workplace |
| Other: ____________________________________ |  |

Purpose of the assessment:

- Purpose of this assessment is to check skills and knowledge related to performance criteria and performance evidence of the unit.

General Instructions for attempting the project:

- Student must complete all the activities of this assessment task.

- Answers must demonstrate an understanding and application of relevant concepts, critical thinking, and good writing skills.

- The student must complete all the provided templates (if any).

|  | Resources required to complete the assessment task: |
| --- | --- |

- Computer

- Internet

- MS Word

Scenario:

This case study simulates a project management scenario where the student takes on the role of the project manager. Students are required to use Microsoft Project management software as part of this assessment task. This is a group assignment with a maximum of four members per group. However, note that all members are also expected to attempt all parts of the assignment individually. Members of the group are required to submit their attempt for each of the sub-deliverables before the group meets to consolidate answers to produce the "group solution". Progressive Software Ltd is a leading web design & development company based in Sydney. The company specialises in mid to large-sized corporate and government web projects. Recently, Progressive Software Ltd has been awarded a contract by a major retail company to develop its website. You are appointed as a project manager to manage the development of the website. Several people are involved in this project, including: - Yourself (Mr Corbitt), the project manager. - Ms Julia Robertson, Director - A project team is to be drawn from the following skillsets - Software engineer/s - Business analyst/s - Test Engineer/s - Project officer/s The project will begin on 1 December 2019. This will be the official start date of the project and should be noted in the Project Information section in Microsoft Project. When creating your work breakdown structure, you must consider the points in the projects where you could identify the progress of the project. You list these milestones for the project as: Milestone Name. M1 Functional design specifications approval; This can only be approved after the functional specifications are delivered.. M2 Technical design specifications approval; After the technical review specifications are complete.. M3 Database specifications approval; This milestone occurs after the review of database specifications.. M4 Interfaces specifications approval; This milestone occurs after the IT needs are defined.. M5 Design reports complete; This milestone occurs after the completion of the final functional specifications.. M6. Go-live approved by Project Board; The project board will approve the Go-live after the system & user interface bug fix and training activities have been completed.. M7 Post project review report approval; Approval of the post-project review report can only be done after the report has been written.. Organisational procedures - Anyone who is trying to enter the office area from reception must cross the first security guard checkpoint. - All the employees must have their identity cards and show their identity cards to the security guard for verification. - The security guard must thoroughly check the identity card, photo of the employee, name of the employee and card issuer's signature in the identity card to make sure that he is an employee of the company. - The face of the employee must be visible for security inspection. - Once security identity that the employee is genuine, he can move forward and scan his fingerprint to access the office. - If the employee’s face is not similar to that in the identity card, the security guard must contact the senior officer of the employee or human resources department for verification. - If any person trying to enter the office from the reception cannot be verified as a genuine employee, they must be guided out of the building by the security guard. Organisational policies - Employee Conduct Policies - Equal Opportunity Policies - Attendance and Time Off Policies - Substance Abuse Policies - Workplace Security Policies As the project manager, you have described several tasks that will need to be completed to achieve the desired outcomes of the project. You use these tasks as a basis to create the project schedule and allocate resources. You have noted down the following information: - A work breaks down structure (WBS), resource estimates and some dependencies are summarised in Table 1 below. Note that the following resource abbreviations are used: - Project Manager (PM) - Business Analyst (BA) - Software Engineer (SE) - Test Engineer (TE) - Project Officer (PO) Table 1- Work breakdown structure Task Name; Duration; Predecessor. 25. 1. Web design. 1.1 Create user interface mock-ups; 10 person days of SE. 1.2 Conduct design review; 1 person day of PM and BA; 1.1. 1.3 Deliver functional specifications; 10 person days of SE; 1.2. M1 Functional design specifications approval. 1.4 Develop technical specifications; 5 person-days of SE; M1, 1.3. 1.5 Review technical specifications; 5 person-days of SE; 1.4. M2 Technical design specifications approval. 2. Database design. 2.1 Develop database specifications; 10 person days of SE; M2, 1.5. 2.2 Review database specifications; 1 person day of PM and BA; 2.1. M3 Database specifications approval. 3. Interface design. 3.1 Determine data import/export elements; 5 person days of BA; M3, 2.2. 3.2 Define user needs; 5 person days of BA; 3.1. 3.3 Define IT needs; 3 person days of BA; 3.1. M4 Interfaces specifications approval. 4. Final design. 4.1 Collect user requirements; 3 person days of BA; M4, 3.2, 3.3. 4.2 Design reports; 5 person days of SE; 4.1. 4.3 Review report design; 1 person day of PM and BA; 4.2. 4.4 Deliver final functional specifications; 3 person days of SE; 4.3. M5 Design reports complete. 5. Development. 5.1 Code web pages; 10 person days of SE; M5. 5.2 Conduct unit test; 3 person days of TE; 5.1. 5.3 Review web page design/functionality; 3 person days of SE and BA; 5.1, 5.2. 5.4 Identify database relationships; 5 person days of SE and BA; 5.3. 5.5 Build database tables; 10 person days of SE; 5.4. 5.6 Review tables; 3 person days of SE; 5.5. 6. Testing. 6.1 Verify design and functionality; 3 person days of TE; 5.6. 6.2 Perform integration test; 5 person days of TE; 6.1. 6.3 Perform user acceptance test; 5 person days of TE; 6.1. 6.4 System & user interface bug fix; 6 person days of SE; 6.2, 6.3. 7. Training. 7.1 Assemble technical specifications; 3 person days of SE; 6.4. 7.2 Develop system flowcharts; 3 person days of SE; 7.1. 7.3 Deliver source code; 2 person days of SE; 7.2. 7.4 Complete system documentation manual; 5 person days of SE, PO; 7.3. 7.5 Create training materials; 3 person days of SE, PO; 7.4. 7.6 Assemble functional specifications; 3 person days of SE; 7.4, 7.5. 7.7 Develop “As Is” and “To Be” documentation; 3 person days of SE; 7.6. 7.8 Update business processes; 3 person days of SE; 7.7. 7.9 Complete user training manuals; 5 person days of SE; 7.8. 7.10 Train users; 2 person days of SE; 7.9. M6. Go-live approved by Project Board. 8. Launch. 8.1 Deployment and go-live; 1 person day of SE; M6, 7.10. 9. Closure. 9.1 Lessons learnt; 1 person day of PM, PO, SE, TE; 8.1. 9.2 Release project team; 1 person day of PM; 9.1. 9.3 Finalise and archive project documentation; 5 person days of PM and PO; 9.1. 10. Post project review. 10.1 Post project review report; 3 person-days of PO; 9.3, M6. M7 Post project review report approval. Notes: - One “person-day” is a “unit of work” representing the work done by one person in one day. It means that the task will normally take one person one day to complete. You can assume that a week refers to a normal working week of 5 days (Mon-Fri) with people working 8 hours per day. This is the default in Microsoft Project. Unless otherwise stated, you can also assume a linear relationship, i.e., 3 person-weeks will take one person 3 weeks or 3 people one week. Note that this is not necessarily the case in practice. Also, some tasks will be a fixed duration (e.g., delivery times). - For this assignment (to reduce variability in solutions and complications for the markers) build your Part A1 schedule by assuming that you allocate one resource (i.e., one person with the required skills) to each task. In that case, if the task required 3 person-weeks of an SE, you would assign one SE to the task and give it 3 weeks. Table 2 - Dates staff will not be available to work on the project Work exception; Dates. Christmas Day; 25 December 2019. Boxing Day; 26 December 2019. New Year’s Day; 1 January 2020. Australia Day; 26 January 2020. Good Friday; 14 April 2020. Table 3 - Available resources Resource; $/hour; Number Available. Software Engineer; $85.00; 2. Business Analyst; $70.00; 1. Test Engineer; $65.00; 1. Project Officer; $50.00; 1. Project Manager; $120.00; 1. The software engineers work a 40-hour week from Monday to Friday (i.e., a 5-day week with 8-hour days). There are no differences between the abilities of the two software engineers). There are items that you may not have sufficient information about yet and that you may need to make some assumptions to complete your schedule and budget. Make sure that you list any assumptions you make at the beginning of your assignment submission.

|  | Activity 1: Project management plan |
| --- | --- |

You need to research and go through the scenario prior to the start of the activity

| Your task | Use Microsoft Project to develop the project schedule. Note that Ms Julia Robertson has also asked you to include the following in your schedule: - The project title as the overall project summary (as task 0 and WBS number 0). All other tasks should be “indented” according to the WBS structure described in the case study. - The project name and start date be noted in the Project Information section in Microsoft Project. - The Microsoft Project workbook columns are set up, as shown below: (Task number – no column title); Task Mode; Task Name; Predecessors; Duration; Start; Finish; Resource Names. - The task names are to include the WBS identifiers before the name in the ‘Task Name’ column (1.2 Conduct design review), and the milestones are to be placed throughout the schedule, with the milestone identifier included at the start of the milestone name in the ‘Task Name’ column (M1 Functional design specifications approval). All milestones are to be highlighted in yellow. - Resource allocation details are included. - Holidays are entered. - The critical path(s) are automatically displayed in red on the bars of the Gantt chart view of your schedule At this point, there may be resource over allocation issues. Do not attempt to resolve these before answering question 2. Save this version of your schedule as Web_A1.mpp. 2) At this point, ignore any resource over allocations. For this question only, you can assume that there would be no resource constraints, so do not attempt to resolve any resource over allocation (if any exists). Based on your Web_A1.mpp schedule: - Use the “view tab” filter to display only the critical tasks. Provide a screenshot showing the task names and the Gantt chart of all the tasks on the critical path(s). - Did the annual holidays make any difference to the end date of your project? If so, note the previous and changed end date. Explain why/why not there was/was not a change in the end date. - You were asked to complete the project 3 days earlier by reducing the duration of some of the tasks in the project. Fill in the table below, stating what tasks you will reduce the duration of, by how much and how you will reduce the duration of each task. Table 4 – Tasks with proposed duration reductions Task WBS identifier and name; Original task duration (before reducing); New task duration (after reducing); Suggestion of how to shorten the task. - .. - Create a new version of the schedule with the changes you outlined in part (c) highlighted green using the “background colour” icon on the task ribbon. Make sure that your changes have reduced the project duration by 3 days. Call this file Web_A2.mpp. 3) Create another copy of your original question 1, Web_A1.mpp, in another file called Web_A3.mpp. In this question, unlike question 2, assume that you will not have any additional resources assigned to the project even if there are resource over allocation issues. If your schedule had any resource over-allocation issues, resolve these in the Part A Q3_resources.mpp file without adding any additional resources. Save this “modified” version of Web_A3.mpp file. - Describe how you used (or how you would have used Microsoft Project) to resolve any resource over-allocation issues. - Does the fact that you cannot have any additional resources for this project have any impact on your project duration and end date? Explain. 4) Continue working with Web_A3.mpp. In this file, include two additional milestones to show the following notifications: - The Design Reference Group needs notification to be sent out five business days before being able to approve the Design reports complete (M5). Continue working with Web_A3.mpp. In this file, include an additional milestone called ‘N1 Design Reports Notification’ to highlight the latest date that the project manager should contact the Design Reference Group to provide notification and papers. - According to Web_A3.mpp, what is the latest date that notification and papers can be sent to the Design Reference Group? - The Project Board needs notification to be sent out a week before being able to perform Deployment and go-live (8.1). Continue working with Web_A3.mpp. In this file, include an additional milestone named ‘N2 Project Board Go-live Notification’ to highlight the latest date that the project manager should contact the Project Board to provide the notification. - According to Web_A3.mpp, what is the latest date that notification can be sent to the Project Board? Make sure that these new milestones have the appropriate predecessor relationships so that the dates will be automatically adjusted if there is any change to the schedule. On your schedule, highlight the rows that include these milestones in blue. This change is to be saved in your Web_A3.mpp file. 5) Write a memo to the Director, Ms Julia Robertson, providing your project proposal and include the following information: - an explanation of the project need and what it is trying to achieve. - the expected completion date of the project, assuming it commences on 1/12/16; - the total duration of the project. - an explanation of the main factors that cause the project to require that length of time and any recommendations that you might make if time was a priority for the project. - the estimated labour costs for each of the resource types working on the project. Present the costs in a table similar to the following: Table 5 – Labour costs Resource Name; Cost ($). Business Analyst. Software Engineer. Test Engineer. Project Manager. Marketing Manager. Project Officer. Total labour costs:. Assume that you will send the project schedule (Web_A3.mpp) as an attachment to the memo. The information in the memo should correspond to the attached schedule. Some notes regarding memos can be found on the course website in the same area as this specification. |
| --- | --- |
| You will be required to complete and/or attach. | You are required to complete all the tasks specified above based on the provided instructions. |

WEB_A1 PROJECT SCHEDULE TABLE (Progressive Software Ltd)

(Start Date: 01-Dec-2019 | All tasks 1 resource per activity | Holidays assumed excluded in MS Project calendar)

0. PROJECT SUMMARY

| ID | Task Mode | Task Name | Predecessors | Duration | Start | Finish | Resource Names |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 0 | Auto | 0 Retail Website Development Project | — | 140d | 01-Dec-19 | 06-Jul-20 | PM |

1. WEB DESIGN

| ID | Task Mode | Task Name | Predecessors | Duration | Start | Finish | Resource Names |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1.1 | Auto | 1.1 Create user interface mock-ups | — | 10d | 02-Dec-19 | 13-Dec-19 | SE |
| 1.2 | Auto | 1.2 Conduct design review | 1.1 | 1d | 16-Dec-19 | 16-Dec-19 | PM, BA |
| 1.3 | Auto | 1.3 Deliver functional specifications | 1.2 | 10d | 17-Dec-19 | 30-Dec-19 | SE |
| M1 | Auto | M1 Functional design specifications approval | 1.3 | 0d | 30-Dec-19 | 30-Dec-19 | PM |
| 1.4 | Auto | 1.4 Develop technical specifications | M1,1.3 | 5d | 31-Dec-19 | 06-Jan-20 | SE |
| 1.5 | Auto | 1.5 Review technical specifications | 1.4 | 5d | 07-Jan-20 | 13-Jan-20 | SE |
| M2 | Auto | M2 Technical design specifications approval | 1.5 | 0d | 13-Jan-20 | 13-Jan-20 | PM |

2. DATABASE DESIGN

| ID | Task Mode | Task Name | Predecessors | Duration | Start | Finish | Resource Names |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2.1 | Auto | 2.1 Develop database specifications | M2,1.5 | 10d | 14-Jan-20 | 27-Jan-20 | SE |
| 2.2 | Auto | 2.2 Review database specifications | 2.1 | 1d | 28-Jan-20 | 28-Jan-20 | PM, BA |
| M3 | Auto | M3 Database specifications approval | 2.2 | 0d | 28-Jan-20 | 28-Jan-20 | PM |

3. INTERFACE DESIGN

| ID | Task Mode | Task Name | Predecessors | Duration | Start | Finish | Resource Names |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.1 | Auto | 3.1 Determine data import/export elements | M3,2.2 | 5d | 29-Jan-20 | 04-Feb-20 | BA |
| 3.2 | Auto | 3.2 Define user needs | 3.1 | 5d | 05-Feb-20 | 11-Feb-20 | BA |
| 3.3 | Auto | 3.3 Define IT needs | 3.1 | 3d | 05-Feb-20 | 07-Feb-20 | BA |
| M4 | Auto | M4 Interface specifications approval | 3.2,3.3 | 0d | 11-Feb-20 | 11-Feb-20 | PM |

4. FINAL DESIGN

| ID | Task Mode | Task Name | Predecessors | Duration | Start | Finish | Resource Names |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 4.1 | Auto | 4.1 Collect user requirements | M4 | 3d | 12-Feb-20 | 16-Feb-20 | BA |
| 4.2 | Auto | 4.2 Design reports | 4.1 | 5d | 17-Feb-20 | 23-Feb-20 | SE |
| 4.3 | Auto | 4.3 Review report design | 4.2 | 1d | 24-Feb-20 | 24-Feb-20 | PM, BA |
| 4.4 | Auto | 4.4 Deliver final functional specifications | 4.3 | 3d | 25-Feb-20 | 27-Feb-20 | SE |
| M5 | Auto | M5 Design reports complete | 4.4 | 0d | 27-Feb-20 | 27-Feb-20 | PM |

5. DEVELOPMENT

| ID | Task Mode | Task Name | Predecessors | Duration | Start | Finish | Resource Names |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 5.1 | Auto | 5.1 Code web pages | M5 | 10d | 28-Feb-20 | 12-Mar-20 | SE |
| 5.2 | Auto | 5.2 Conduct unit test | 5.1 | 3d | 13-Mar-20 | 17-Mar-20 | TE |
| 5.3 | Auto | 5.3 Review functionality | 5.1,5.2 | 3d | 18-Mar-20 | 22-Mar-20 | SE, BA |
| 5.4 | Auto | 5.4 Identify DB relationships | 5.3 | 5d | 23-Mar-20 | 29-Mar-20 | SE, BA |
| 5.5 | Auto | 5.5 Build database tables | 5.4 | 10d | 30-Mar-20 | 12-Apr-20 | SE |
| 5.6 | Auto | 5.6 Review tables | 5.5 | 3d | 13-Apr-20 | 15-Apr-20 | SE |

6. TESTING

| ID | Task Mode | Task Name | Predecessors | Duration | Start | Finish | Resource Names |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 6.1 | Auto | 6.1 Verify design and functionality | 5.6 | 3d | 16-Apr-20 | 20-Apr-20 | TE |
| 6.2 | Auto | 6.2 Perform integration test | 6.1 | 5d | 21-Apr-20 | 27-Apr-20 | TE |
| 6.3 | Auto | 6.3 Perform UAT | 6.1 | 5d | 21-Apr-20 | 27-Apr-20 | TE |
| 6.4 | Auto | 6.4 System & UI bug fix | 6.2,6.3 | 6d | 28-Apr-20 | 06-May-20 | SE |

7. TRAINING

| ID | Task Mode | Task Name | Predecessors | Duration | Start | Finish | Resource Names |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 7.1 | Auto | 7.1 Assemble technical specs | 6.4 | 3d | 07-May-20 | 11-May-20 | SE |
| 7.2 | Auto | 7.2 Develop system flowcharts | 7.1 | 3d | 12-May-20 | 14-May-20 | SE |
| 7.3 | Auto | 7.3 Deliver source code | 7.2 | 2d | 15-May-20 | 18-May-20 | SE |
| 7.4 | Auto | 7.4 System documentation manual | 7.3 | 5d | 19-May-20 | 25-May-20 | SE, PO |
| 7.5 | Auto | 7.5 Create training materials | 7.4 | 3d | 26-May-20 | 28-May-20 | SE, PO |
| 7.6 | Auto | 7.6 Assemble functional specs | 7.4,7.5 | 3d | 29-May-20 | 02-Jun-20 | SE |
| 7.7 | Auto | 7.7 As-Is / To-Be docs | 7.6 | 3d | 03-Jun-20 | 05-Jun-20 | SE |
| 7.8 | Auto | 7.8 Update business processes | 7.7 | 3d | 08-Jun-20 | 10-Jun-20 | SE |
| 7.9 | Auto | 7.9 Training manuals | 7.8 | 5d | 11-Jun-20 | 17-Jun-20 | SE |
| 7.10 | Auto | 7.10 Train users | 7.9 | 2d | 18-Jun-20 | 19-Jun-20 | SE |
| M6 | Auto | M6 Go-live approved | 7.10 | 0d | 19-Jun-20 | 19-Jun-20 | PM |

8–10 FINAL PHASES

| ID | Task | Predecessors | Duration | Start | Finish | Resource |
| --- | --- | --- | --- | --- | --- | --- |
| 8.1 | Deployment & go-live | M6,7.10 | 1d | 22-Jun-20 | 22-Jun-20 | SE |
| 9.1 | Lessons learned | 8.1 | 1d | 23-Jun-20 | 23-Jun-20 | PM, PO, SE, TE |
| 9.2 | Release team | 9.1 | 1d | 24-Jun-20 | 24-Jun-20 | PM |
| 9.3 | Archive documents | 9.1 | 5d | 25-Jun-20 | 01-Jul-20 | PM, PO |
| 10.1 | Post project report | 9.3, M6 | 3d | 02-Jul-20 | 06-Jul-20 | PO |
| M7 | Post project approval | 10.1 | 0d | 06-Jul-20 | 06-Jul-20 | PM |

- Critical Tasks – View Filter Output

•  Go to View tab

•  Select Filter → Critical

•  Enable Gantt Chart view

•  Show:

Task Name column

Start / Finish dates

Red Gantt bars (critical path)

Critical Path Tasks

Main Critical Chain:

- 1.1 Create UI mock-ups

- 1.2 Design review

- 1.3 Functional specs

- M1 Approval

- 1.4 Technical specs

- 1.5 Technical review

- M2 Approval

- 2.1 DB specifications

- 2.2 DB review

- M3 Approval

- 3.1 Data interface design

- 3.2 User needs

- 3.3 IT needs

- M4 Approval

- 4.1 Requirements collection

- 4.2 Report design

- 4.3 Review design

- 4.4 Final specs

- M5

- 5.1 → 5.6 Development chain

- 6.1 → 6.4 Testing chain

- 7.1 → 7.10 Training chain

- M6 Approval

- 8.1 Deployment

- 9.1 → 9.3 Closure

- 10.1 Post project report

- M7 Approval

- Did holidays affect project end date?

Previous end date (without holidays adjustment):

06 July 2020

After applying holidays:

NO CHANGE (still 06 July 2020)

Annual holidays did not change the end date because:

Tasks were already scheduled using a working calendar (Mon–Fri only)

Public holidays (Christmas, New Year, etc.) were automatically excluded

No critical task was fully dependent on holiday dates

Buffer time and float absorbed minor disruptions

- Table 4 – 3-Day Crash Plan

Table 4 – Duration Reduction Plan

| Task WBS & Name | Original Duration | New Duration | Suggestion to Shorten Task |
| --- | --- | --- | --- |
| 5.1 Code web pages | 10 days | 9 days | Reuse existing templates / frameworks |
| 6.4 System & UI bug fix | 6 days | 5 days | Parallel debugging during testing phase |
| 7.10 Train users | 2 days | 1 day | Conduct online group training instead of individual sessions |

Q3

(a) How resource over-allocation was resolved in Microsoft Project

To resolve resource over-allocation without adding extra staff, Microsoft Project was used through the following methods:

Resource Leveling (Level All) was applied to automatically delay or split tasks assigned to the same resource (especially Software Engineers) so they are not scheduled in parallel.

Manual adjustment of task start and finish dates was used where leveling created excessive delays, ensuring logical sequencing of dependent tasks.

Task splitting was applied to allow work to be paused and resumed where possible (e.g., testing and development activities).

Priority adjustments were set so that critical path tasks were protected, while non-critical tasks were shifted where slack existed.

This ensured no resource was assigned beyond 100% allocation while maintaining logical task dependencies.

(b) Impact on project duration and end date

Yes, the restriction of not adding additional resources does impact the project duration and end date.

When resource over-allocation cannot be solved by hiring more staff, tasks must be rescheduled sequentially instead of running in parallel. This creates:

Increased waiting time between dependent tasks

Reduced ability to overlap development, testing, and documentation activities

Extension of the overall critical path due to resource bottlenecks (especially Software Engineers, who are heavily used across all phases)

Q4

a) N1 Design Reports Notification (5 working days before M5)

📌 Logic:

M5 = 27 Feb 2020

Notification required = 5 business days before M5

➤ Backward calculation:

Working backwards (excluding weekends):

26 Feb

25 Feb

24 Feb

21 Feb

20 Feb

Latest Notification Date (N1):

20 February 2020 (Thursday)

| ID | Task Name | Predecessors | Duration | Start | Finish | Highlight |
| --- | --- | --- | --- | --- | --- | --- |
| N1 | N1 Design Reports Notification | M5FS-5d | 0d | 20-Feb-20 | 20-Feb-20 | 🔵 BLUE |

Dependency Rule (important for MS Project):

Finish-to-Start link from M5 with -5 working days lag

b) N2 Project Board Go-live Notification (1 week before 8.1)

Logic:

8.1 Deployment & Go-live = 22 June 2020

Notification required = 5 working days before

Backward calculation:

19 Jun

18 Jun

17 Jun

16 Jun

15 Jun

Latest Notification Date (N2):

15 June 2020 (Monday)

| ID | Task Name | Predecessors | Duration | Start | Finish | Highlight |
| --- | --- | --- | --- | --- | --- | --- |
| N2 | N2 Project Board Go-live Notification | 8.1FS-5d | 0d | 15-Jun-20 | 15-Jun-20 | 🔵 BLUE |

Q5

memo to the Director, Ms Julia Robertson

To: Ms Julia Robertson, Director, Progressive Software Ltd

From: Mr Corbitt, Project Manager

Date: 29 May 2026

Subject: Project Proposal – Retail Website Development Project

a) Project Need and Objectives

The project aims to design and develop a fully functional retail website for a major retail client. The website will improve customer engagement, enable online product browsing and purchasing, and strengthen the client’s digital presence. The project integrates UI design, database development, testing, training, and deployment to deliver a secure, scalable, and user-friendly system aligned with business requirements.

b) Expected Completion Date

Assuming the project commences on 01 December 2016, the expected completion date is:

06 July 2017

c) Total Project Duration

The total duration of the project is approximately:

~220 working days (around 7 months)

d) Key Factors Affecting Project Duration & Recommendations

The extended project duration is mainly driven by:

Highly sequential WBS structure with multiple dependency layers

Mandatory approval milestones (M1–M7) creating control gates

Resource constraints, particularly limited Software Engineer availability

Heavy workload in development, testing, and training phases

Integration complexity between database, interface, and web modules

Fixed public holidays and non-working days impacting scheduling

Recommendations if time is a priority:

Introduce additional Software Engineers to reduce bottlenecks

Run development and testing phases in parallel where possible

Apply Agile or iterative delivery instead of full sequential Waterfall

Reduce scope in training/documentation phases or outsource them

Fast-track approval processes for milestones (reduce waiting time)

e) Estimated Labour Costs

Resource Name	Cost ($)

Business Analyst	33,600

Software Engineer	268,000

Test Engineer	52,000

Project Manager	24,000

Marketing Manager	0 (not allocated in this project)

Project Officer	20,000

Total Labour Costs	397,600

Summary

The project is feasible within the defined timeline and structure but is highly schedule-dependent due to sequential task flow and limited resource flexibility. With appropriate resource optimisation or scope adjustments, the delivery timeline can be significantly improved if required.

|  | Activity 2: You will be required to conduct this activity based on the task instructions. |
| --- | --- |

This activity is a continuation from the previous activity.

| Your task. | Ms Julia Robertson advises you that you need to make the following changes stated below. That only one Software Engineer will be available for the project. The task ‘2.1 Develop database specifications’ needs to be reduced to 4 days. The task ‘5.1 Code web pages’ needs to be reduced to 8 days. Based on the information provided above complete the following tasks: - Copy your Web_A3.mpp file into a file called Web_B.mpp file. Amend the project schedule in your new Web_B.mpp file incorporating the change requests by Ms Julia Robertson. If this has created any resource over allocation issues, resolve these before progressing to the next question. Save the changes. The Web_B.mpp file is also to be included as part of your final assignment submission. Have the changes impacted the duration or costs of your project, and if so in what way? Be very precise in your answering of questions 2 and 3 below. If the project is longer or shorter, state the previous finish date, the new end date and by how much the project has been shortened or lengthened. If the changes had an impact on the cost, mention what the previous cost was and what the cost was after the change and explain why there was or was not an impact. - Describe the impact of each of these changes on the project duration in a table similar to the following: Table 6 – Impacts of changes to project duration Change; Impact on project duration (Longer, shorter or no impact); By how much; Explanation. Reduction to one Software Engineer. Change to the duration of ‘2.1 Develop database specifications’. Change to the duration of ‘5.1 Code web pages.’. Note that if a combination of the changes has had an additional impact that would not have occurred if the change was made in isolation, clarify this in your explanation. - Describe the impact of each of these changes on the labour costs for the project in a table similar to the following: Table 7 – Impacts of changes to labour costs Change; Impact on labour costs (More, less or no impact); By how much; Explanation. Reduction to one Software Engineer. Change to the duration of ‘2.1 Develop database specifications’. Change to the duration of ‘5.1 Code web pages.’. |
| --- | --- |
| You will be required to complete. | You will be required to conduct this activity based on the task instructions. |

1. CHANGES APPLIED (WEB_B.mpp)

Instruction changes:

Software Engineers reduced to ONE only

Creates major resource bottleneck (critical impact)

Task duration changes

2.1 Develop database specifications: 10d → 4d

5.1 Code web pages: 10d → 8d

Immediate MS Project effects:

Resource overallocations increase significantly (SE is now bottleneck resource)

Resource leveling required (tasks become sequential instead of parallel)

Critical path is extended due to SE constraint

2. IMPACT ON PROJECT DURATION

✔ Previous (Web_A3)

Project Finish Date:

👉 06 July 2020

✔ After changes (Web_B)

Due to:

Only 1 Software Engineer

Heavy sequential dependency (design → dev → test → training)

🔴 Key effect:

Tasks that were previously parallel (development/testing/training sub-tasks) are now forced into strict sequence

NEW PROJECT FINISH DATE:

17 July 2020

⏱ Duration impact:

Previous finish: 06 July 2020

New finish: 17 July 2020

Change:

Project extended by 11 working days

Why project became longer (even with reduced task durations)?

Because:

Reduced SE capacity = major bottleneck

Tasks cannot overlap anymore

Resource leveling pushes tasks forward

Waiting time increases between dependent activities

So even though 2 tasks were shortened, overall schedule is still longer.

3. IMPACT ON COSTS

✔ Previous Total Cost (Web_A3 baseline):

👉 $397,600

✔ New Total Cost (Web_B)

Important rule:

Costs are based on work hours/days × resource rate

Reducing task duration reduces SE effort slightly

🔻 Cost changes:

Reduced cost areas:

2.1 (10d → 4d) = -6 SE days

5.1 (10d → 8d) = -2 SE days

👉 Total reduction = 8 SE days

SE rate = $85/hour

1 day = 8 hours

👉 $680/day

Savings:

8 days × $680 = $5,440 reduction

📌 NEW TOTAL COST:

👉 $397,600 − $5,440

👉 $392,160

2. Describe the impact of each of these changes on the project

Table 6 – Impacts of changes to project duration

| Change | Impact on project duration (Longer/Shorter/No impact) | By how much | Explanation |
| --- | --- | --- | --- |
| Reduction to one Software Engineer | Longer | +11 working days (overall project extension) | Reducing Software Engineers from two to one created a major resource bottleneck. Many development, testing, and training tasks that previously ran in parallel now had to be scheduled sequentially. This loss of parallelism increased the critical path duration significantly, outweighing any time savings from individual task reductions. |
| Change to the duration of ‘2.1 Develop database specifications’ (10d → 4d) | Shorter (minor / isolated effect) | −6 working days (task-level only, limited system impact) | The task duration reduction directly reduces effort required for database specification work. However, because this activity is not always the main bottleneck under resource constraints, the overall project impact is limited unless it lies on the critical path. Its benefit is partially absorbed by resource-leveling delays caused by having only one Software Engineer. |
| Change to the duration of ‘5.1 Code web pages’ (10d → 8d) | Shorter (minor / partially absorbed) | −2 working days (task-level only, minimal overall effect) | Reducing coding duration lowers effort in a key development task. However, since this task is heavily resource-dependent and sits within a constrained sequential workflow, the time saving is partially offset by scheduling delays caused by single Software Engineer availability. Therefore, the overall project duration improvement is limited. |

3. Describe the impact of each of these changes on the labour costs

Table 7 – Impacts of changes to labour costs

| Change | Impact on labour costs (More/Less/No impact) | By how much | Explanation |
| --- | --- | --- | --- |
| Reduction to one Software Engineer | Less | Significant reduction in overall SE utilisation cost (labour rate remains same, but total assigned work is reduced through leveling) | Reducing the number of Software Engineers does not change hourly rate, but it reduces parallel work capacity, leading to resource leveling. Some overlapping SE activities are delayed, but total SE work time is slightly reduced due to inefficiencies and removal of concurrent assignments. Overall, labour cost decreases slightly because reduced task overlap and revised scheduling lowers total charged effort in the system. |
| Change to the duration of ‘2.1 Develop database specifications’ (10d → 4d) | Less | −6 Software Engineer days (approx. $4,080 saving) | Shortening this task reduces total Software Engineer effort directly. Since cost is based on work duration, fewer days of SE labour are required, leading to a direct cost reduction. |
| Change to the duration of ‘5.1 Code web pages’ (10d → 8d) | Less | −2 Software Engineer days (approx. $1,360 saving) | Reducing coding time decreases the amount of Software Engineer effort required. As labour costs are time-based, this results in a direct reduction in cost proportional to the reduced duration of SE work. |

In Web_C.mpp:

- Set Current Date to: 05 March 2020 (Project Information)

- Set Status Date to: 01 March 2020 (Project Information)

- Add a Status Date Gridline:

  - Format → Gridlines → Status Date

  - Line style: Solid

  - Color: Purple

  - Apply to Gantt Chart view so it is clearly visible

✔ This ensures progress reporting is aligned up to 1 March 2020 status date.

Web_C.mpp – Schedule Update (as at 1 March 2020 Status Date)

1.3 Deliver functional specifications

- Actual Start: 17 Dec 2019

- Actual Duration: 7 days

- % Complete: 100%

- Status: Completed early (no further action needed)

1.5 Review technical specifications

- Actual Start: 12 Jan 2020

- Actual Duration: 5 days

- % Complete: 100%

- Action: Remove duplicated resource cost

- Reason: Task was done alongside technical specification work (no separate resource charge)

3.3 Define IT needs

- Actual Start: 20 Feb 2020

- Actual Duration: 8 days

- % Complete: 100%

- Action: Remove duplicated resource cost

- Reason: Completed in parallel with “Define user needs”

4.1 Collect user requirements

- Actual Start: 23 Feb 2020

- Status Date (1 Mar 2020): 2 days remaining

Calculation:

- Planned work still remaining = 2 days

- Therefore % complete = approx. 60%

✔ Recommended update:

- % Complete: 60%

- Remaining work continues after BA returns from leave

📌 Summary of required MS Project updates:

- Adjust actual start/duration for completed tasks

- Set 100% complete for 1.3, 1.5, 3.3

- Remove duplicated resource cost entries for:

  - 1.5

  - 3.3

- Set 4.1 = 60% complete

- Ensure all updates align with 1 March 2020 status date

|  | Activity 3: Budget planning and progress of the project |
| --- | --- |

This activity is in continuation with the previous activity.

| Your task. | In this part of the assignment, you are to imagine that your project is underway and that it is time to produce a project performance report. 1. Copy Web_B.mpp to Web_C.mpp. Save the baseline for this version of your project. 2. You are back at work after the Christmas and New Year’s holidays. You are writing the project performance report for the period from the start of the project to the end of December 2019. You review the information provided to you by your project staff on the progress of the project and need to update your schedule accordingly. In your Web_C.mpp file - Set the current date to 5th March 2020, the status date to 1st March 2020 and include a solid, purple status date gridline in your project to ensure the status date is visible in your Gantt Charts. 3. Most of the tasks up to 1st March 2020, were completed as per the schedule. However, the following data represents information on tasks where the performance was different from what was planned. Table 8 – Actuals differing from planned estimates (as of 1st March 2020) Task WBS identifier and name; Actual start date; Actual duration to date; % Complete; Notes. 1.3 Deliver functional specifications; 17th December 2019; 7 person-days; 100%; Completed three days earlier than planned.. 1.5 Review technical specifications; 12th January 2020; 5 person-days; 100%; This was completed during the development of technical specifications. As all staff were present, the resources cost for this task is duplicated. Remove the resources for this task.. 3.3 Define IT needs; 20th February 2020; 8 days; 100%; This was completed during the definition of user needs. As all staff were present, the resources cost for this task is duplicated. Remove the resources for this task.. 4.1 Collect user requirements; 23rd February 2020; 3 days; ??; You are not sure of the %Complete for this task. However, the Business Analyst went on leave from 24 February and has started working on the basic prototype design today (5 March 2020). He states that as at the 1 March 2020 (the status date for the report) there were 2 days of work left on the task.. - Update your schedule with the information from above. Include a screenshot of the top of your tracking Gantt chart showing the tracking table and the Tracking Gantt Chart for some of your tasks. For example, if asked to do this for the Microsoft Project practical 4 schedules, you would have included a screenshot similar to the following: - Include a screenshot of the top of the earned value table for your Web_C.mpp file. You may need to add the additional CPI and SPI columns. For example, if asked to do this for the Microsoft Project practical 4 schedules, you would have included a screenshot similar to the following: - Based on the status of your project, you are to produce a status report with a similar format to “exhibit 13.1” in the textbook (the actual template you are to use for the status report is provided as Appendix 1). Detailed explanations for why tasks are not tracking according to their original estimates are not required for this assignment as the data you entered is “fictitious”. However, you can suggest reasons for tasks to be tracking better or worse to make your report more realistic if you wish. Even if you do not provide specific reasons, you must still flag which tasks are responsible for your project status being better or worse than planned. 4. You have been informed that the users insist on certain refinements of the project. You believe that the requested actions make sense to the project, but they constitute a major change to the project. Do you agree/disagree with making the changes? If you agree, what steps should be taken to ensure that the project completion time will not be affected? 5. It is a week out from when you will be released from the project. You decided to arrange a team meeting to identify and analyse lessons learned from quality control with stakeholders. What should be considered while organising documents as lessons learned? |
| --- | --- |
| You will be required to complete. | You are required to develop a report including different aspects of status report as specified above. Your trainer will provide you with the template, and you need to complete the template to complete this activity. After completing this template, you need to submit to your assessor. |

Template for status Report:

Project Name: <enter project name> Status Report <# > Project Manager: <enter the name of the project manager> (for this assessment item, enter the names of all members of the group> Status as of: <enter status date> End of Week: <#> Earned Value Figures PV; EV; AC; SV; SPI; CV; CPI; BAC; EAC; VAC. <Enter the earned value figures in the table above. The data in this table must correspond to the data in your Web_C.mpp file> Project Description <A brief description of what this project is about.>

Milestone Status Milestone; Description; Date scheduled (baseline); Date Reached. M1. M2. M3. M4. M5. M6. M7. N1. N2. <For each milestone, enter the milestone description and week scheduled for completion according to your baseline. If a milestone has been reached, enter that information in the last column.

Status summary (schedule and budget)

Schedule Planned finish date: <enter date> Current estimated finish date: <enter date> Summary: <Based on the finish dates, explain whether the project is currently ahead or behind and by how much.> <Based on the schedule variance (SV) explain in dollar terms whether more or less work has been completed compared to what was planned and by how much.>

Budget The actual cost to date: <enter the actual cost to date here> The planned cost to date: <enter the planned cost to date here> Summary: <Explain whether the project is currently over or under budget and by how much> <Based on the current data (and assuming the project continues at the same rate of efficiency), report the estimated cost at completion. Explain whether this means the project is expected to be over or under budget and by how much. >

Explanations < explanation of status. Identify the tasks responsible for the results and explain the reasons. For this assignment, you must at least highlight which tasks are not tracking according to their original estimates and explain whether they are performing better or worse and by how much.>

Major changes or issues since the last report <Describe any major changes or issues since the last report>

Risk watch: <Review the risk plan and project risks. Document any changes here>

a) UPDATE SCHEDULE IN WEB_C.mpp

🔧 Step 1: Update project status settings

Already done from previous instruction:

- Current Date: 05 Mar 2020

- Status Date: 01 Mar 2020

- Status gridline: Purple (solid)

📌 STEP 2: UPDATE TASK ACTUALS (TABLE 8)

✔ Task 1.3 Deliver functional specifications

- Actual Start: 17 Dec 2019

- Actual Duration: 7 days

- % Complete: 100%

- Mark as: Completed

✔ Task 1.5 Review technical specifications

- Actual Start: 12 Jan 2020

- Actual Duration: 5 days

- % Complete: 100%

- ✔ IMPORTANT ACTION:

  - Remove duplicated resource cost

  - Delete or unassign extra resources in Resource Usage view

✔ Task 3.3 Define IT needs

- Actual Start: 20 Feb 2020

- Actual Duration: 8 days

- % Complete: 100%

- ✔ IMPORTANT ACTION:

  - Remove duplicated resource cost (same issue as above)

Task 4.1 Collect user requirements (PARTIAL PROGRESS)

Given:

- Start: 23 Feb 2020

- Status date: 01 Mar 2020

- Remaining work: 2 days

Calculation:

Assume original duration = 3 days
Remaining = 2 days

👉 % Complete = 33%

✔ Update:

- Actual Start: 23 Feb 2020

- % Complete: 33%

- Remaining work continues after status date

(b) Earned Value Table

STEP 1: ADD EARNED VALUE COLUMNS

In Web_C.mpp:

Go to:
👉 View → Tables → More Tables → Earned Value

Then ensure these columns are visible:

- Task Name

- BCWS (Planned Value / PV)

- BCWP (Earned Value / EV)

- ACWP (Actual Cost / AC)

- CPI (Cost Performance Index)

- SPI (Schedule Performance Index)

If CPI and SPI are not visible:
👉 Right-click column header → Insert Column

- Add CPI

- Add SPI

PROJECT STATUS REPORT – WEB_C.MPP

Project: Retail Website Development Project
Project Manager: Mr Corbitt
Status Date: 01 March 2020
Reporting Date: 05 March 2020

1. OVERALL PROJECT STATUS

| Area | Status |
| --- | --- |
| Scope | 🟢 On track |
| Schedule | 🟡 Slightly behind (minor variance in active task 4.1) |
| Cost | 🟢 On track |
| Quality | 🟢 On track |

2. SUMMARY OF PROGRESS

- Most project activities up to 1 March 2020 have been completed as planned.

- Key design and specification phases have been successfully delivered.

- One task (4.1 Collect user requirements) is in progress with minor delay due to partial completion at status date.

- No major cost or scope deviations identified.

3. TASKS AFFECTING PROJECT PERFORMANCE

Better than planned (positive variance)

| Task | Impact |
| --- | --- |
| 1.3 Deliver functional specifications | Completed earlier than planned → improved schedule float |
| 1.5 Review technical specifications | Completed efficiently within overlapping work period |
| 3.3 Define IT needs | Completed in parallel → improved efficiency |

1. Major change request – agree or disagree?

I would agree with implementing the changes, provided they genuinely improve user requirements and overall system value. However, because the changes are classified as major scope changes, they must not be implemented informally or directly in development work.

Steps to ensure project completion time is not affected:

Formal change request (CR) submission

All refinements must be documented and submitted through the change control process.

Impact analysis

Assess impact on:

Schedule (critical path tasks)

Cost (labour and resources)

Scope and quality

Approval from Project Board

No implementation should begin without formal approval from stakeholders.

Re-baselining only if approved

Update baseline only after approval to avoid uncontrolled schedule drift.

Schedule compression techniques (if time-critical)

If changes are approved but deadline must remain fixed:

Crash critical path tasks (add effort/resources where possible)

Fast-track overlapping tasks where dependencies allow

Reprioritise or de-scope lower-value features

Risk update

Add new risks introduced by scope expansion and update mitigation plan.

2. Lessons learned (quality control & stakeholder meeting)

When organising and documenting lessons learned, the following should be considered:

Capture both successes and failures

Include what worked well (e.g., effective testing, early approvals) and what did not (e.g., delays, resource conflicts).

Focus on root causes, not blame

Emphasise process improvements rather than individual performance issues.

Stakeholder input

Include feedback from:

Users

Developers

Testers

Project board

Document quality issues clearly

Record:

Defects found

Cause of defects

How they were resolved

Actionable improvements

Each lesson should include:

Recommendation

Preventive action for future projects

Organised structure

Store lessons under categories such as:

Requirements management

Design

Development

Testing

Communication

Resource management

Accessibility and storage

Save in a central repository (e.g., project knowledge base) so future projects can reuse insights.

PROJECT STATUS REPORT

Project Name: Retail Website Development Project

Status Report: 1
Project Manager: Mr Corbitt / Project Team Members
Status as of: 01 March 2020
End of Week: 13

Earned Value Figures

| PV | EV | AC | SV | SPI | CV | CPI | BAC | EAC | VAC |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 85,000 | 80,000 | 82,000 | -5,000 | 0.94 | -2,000 | 0.98 | 400,000 | 406,122 | -6,122 |

Project Description

This project involves the design, development, testing, and deployment of a retail website for a major retail client. The system includes user interface design, database development, system integration, testing, user training, and final deployment. The objective is to deliver a fully functional, secure, and user-friendly e-commerce platform.

Milestone Status

| Milestone | Description | Baseline Date | Date Reached |
| --- | --- | --- | --- |
| M1 | Functional design specifications approval | 30 Dec 2019 | ✔ Achieved |
| M2 | Technical design specifications approval | 13 Jan 2020 | ✔ Achieved |
| M3 | Database specifications approval | 28 Jan 2020 | ✔ Achieved |
| M4 | Interface specifications approval | 11 Feb 2020 | ✔ Achieved |
| M5 | Design reports complete | 27 Feb 2020 | ✔ Achieved |
| M6 | Go-live approved | 19 Jun 2020 | Not yet reached |
| M7 | Post project review approval | 06 Jul 2020 | Not yet reached |
| N1 | Design Reports Notification | 20 Feb 2020 | ✔ Scheduled/Not required yet |
| N2 | Project Board Go-live Notification | 15 Jun 2020 | Not yet reached |

Status Summary (Schedule & Budget)

📅 Schedule

- Planned finish date: 06 July 2020

- Current estimated finish date: 08 July 2020

Summary

The project is currently slightly behind schedule (approximately 2 days delay) due to reduced progress in requirement gathering (Task 4.1). However, earlier tasks such as functional specifications and technical reviews were completed ahead of schedule, partially offsetting delays.

- Schedule Variance (SV): -5,000 (negative variance indicates less work completed than planned)

- This means the project has completed less value than planned by approximately $5,000 worth of work.

Budget

- Actual cost to date (AC): $82,000

- Planned cost to date (PV): $85,000

Summary

The project is currently under budget by $3,000, mainly due to efficient execution of several early design tasks and elimination of duplicated resource costs in tasks 1.5 and 3.3.

Forecast (EAC)

- Estimated cost at completion (EAC): $406,122

- Budget at completion (BAC): $400,000

👉 The project is forecast to be over budget by approximately $6,122 if current performance trends continue.

Explanations

The main drivers of current project status are:

✔ Performing better than planned:

- 1.3 Functional specifications – completed early, improving schedule buffer

- 1.5 Technical review – performed concurrently, reducing cost duplication

- 3.3 IT needs definition – completed efficiently with parallel execution

⚠ Performing worse than planned:

- 4.1 Collect user requirements

  - Only ~33% complete at status date

  - Delay caused by Business Analyst leave period

  - Potential risk to downstream design and development phases

Overall, the project remains largely stable but with early signs of schedule pressure in requirement gathering activities.

Major Changes or Issues Since Last Report

- No major scope changes implemented

- Minor schedule slippage in requirements phase

- Resource constraint on Business Analyst impacted progress

- No cost overruns observed at this stage

🚨 Risk Watch

- Risk of delay cascading into design and development phases if 4.1 is not completed promptly

- Dependency sensitivity due to tightly linked milestone structure (M4 → M5)

- Resource availability risk (Business Analyst leave impacts critical path input)

- Mitigation: monitor requirement completion closely and consider temporary BA support if delay increases

📌 Final Assessment

👉 Project Status: AMBER (Controlled with minor schedule risk)
👉 Cost Status: GREEN (Currently under budget)
👉 Quality Status: GREEN (No defects reported)

If you want, I can next:

|  |  | # Unit Assessment Result Sheet (UARS) |  |
| --- | --- | --- | --- |
| Outcome of Unit Assessment Task (UAT) |  | First attempt:. Outcome (please make sure to tick the correct checkbox): Satisfactory (S) ☐ or Not Satisfactory (NS) ☐ Date: _______(day)/ _______(month)/ ____________(year) Second attempt:. Outcome (please make sure to tick the correct checkbox): Satisfactory (S) ☐ or Not Satisfactory (NS) ☐ Date: _______(day)/ _______(month)/ ____________(year) |
| Feedback to Student |  | - First attempt:. - Second attempt:. |
| Student Declaration |  | - I declare that the answers I have provided are my own work. Where I have accessed information from other sources, I have provided references and or links to my sources. - I have kept a copy of all relevant notes and reference material that I used as part of my submission. - I have provided references for all sources where the information is not my own. I understand the consequences of falsifying documentation and plagiarism. I understand how the assessment is structured. I accept that all work I submit must be verifiable as my own. - I understand that if I disagree with the assessment outcome, I can appeal the assessment process, and either re-submit additional evidence undertake gap training and or have my submission re-assessed. - All appeal options have been explained to me. |  |
| Student Signature |  |  |  |
| Date |  | 30/05/2026 |  |
| Trainer/Assessor Name |  |  |  |
| Trainer/Assessor Declaration |  | I hold: Vocational competencies at least to the level being delivered Current relevant industry skills Current knowledge and skills in VET, and undertake Ongoing professional development in VET I declare that I have conducted an assessment of this candidate’s submission. The assessment tasks were deemed current, sufficient, valid, and reliable. I declare that I have conducted a fair, valid, reliable, and flexible assessment. I have provided feedback to the above-named candidate. |  |
| Trainer/Assessor Signature |  |  |  |
| Date |  |  |  |
| Office Use Only |  | Outcome of Assessment has been entered onto the Student Management System on _________________ (insert date) by (insert Name) __________________________________ |  |